CEN ISSS WS/BII

Project template for execution  – Report Annex to WG4 CWA

(Pilot Execution Guidelines)

Version: 0.5

Released: 2009-06-25

Date of approval:

# About this document

This document presents requirements for a Project template and report template. The input for the content of this document is outlined in the “2008_03WG4_Report” document. The purpose of the report is to present requirements for the Project Template and the Project Report. To illustrate possible ways to manifest a project plan, an example is provided at the end of this document.

Note: It is important that this document be reviewed continuously to keep the information relevant and up-to-date. This document is subject to further elaboration.

Table of Content

About this document	2

Summary	5

Scope	5

OBjectives	7

Overview	7

Pilot types, overview	7

Pilot types, details	8

Assumptions	8

Pilot Execution Checklist	9

Legend	11

Building blocks	12

Pilot template Requirements	12

Pilot report	15

Methodology	15

Selecting the Project methodology	16

Development Model	16

Roles	16

Project specific considerations pertinent to the CEN BII WS and PEPPOL	17

The Pilot Execution template & Pilot Report– overview level layout	18

Input	18

Activities	18

Result	19

Exit criteria	19

Overview level process	19

MISCELLANEOUS	20

Pilot Execution Templates	20

Selecting the appropriate content	20

Proof-of-concept Pilot	20

Test Pilot	21

Production pilot	22

General remarks	23

Pilot (Project) Template	24

Instructions	24

Step 1: Select Pilot Type	24

Step 2: SET UP (Pre Pilot)	25

Step 3: Execution	28

Step 4: Post Pilot (Follow up)	29

Pilot (project) report template	29

Project plan Template – alternate Example	31

# Summary

This document provides guidelines for setting up and executing pilot projects. Even though most of what is described and suggested is of a general nature, the content is presented with the PEPPOL project in mind and the assumption that the CEN ISSS BII/WS framework will be used to conduct the pilots.

The Pilot Execution Guidelines also presents a Pilot execution template and a pilot report template.

# Scope

The above picture places the Pilot Execution Guidelines in context.

The Focus is on various forms of Pilots projects, supporting the execution of activities in the best possible way. The guidelines addresses the of the “How” issue. Guiding objectives are cost - whether the pilot project was executed in on budget and on schedule.

It is however important to look at the Guidelines in the above picture as an whole in relation to other CEN ISSS BII deliverables produced to provide Pilot support, namely the;

- Evaluations Guidelines: that provides support to setup and monitor how well the pilots perform based on the key performance indicators linked to the pilots various key element, thus providing valuable feedback on the actual value of the pilot

and the

- Test Guidelines: that provides support to verify the quality of the pilots, primarily measured against the ISSS CEN BII profile architecture. The Test Guidelines’ objective is to secure that any solution (or Pilot) built on the profile framework meets the requirements.

In summary: even though each Guidelines entity serves a specific purpose, the benefit that comes from using individual Guidelines is multiplied when they are used in sync. It is there recommended to please refer to respective Guidelines element when requested to do so.

# OBjectives

## Overview

The objective with this document and its attachments is to provide guidelines for executing pilot projects. The definition as stated in the contract for the WG4 editor states the following:

Development of project report template.

- The creation of guidelines (check list) on how to do project reports – reporting of the effect and results of a pilot projects including lessons learned and experienced problems. The main focus will be on securing quality input and successfully completing the pilots thus making it easier to share knowledge vis-à-vis the pilots.

The linkage with both the deliverable “Lessons Learned” report and the Evaluation & Test Guidelines, respectively, is clear. In order to obtain valuable information from the various pilot types to be executed, it’s essential to both understand how to set up and execute the individual pilot as well as how to go about in order learn from the pilot. In this sense, the Pilot Execution Guidelines provides support for both the actual pilot execution as well as finding a way to secure knowledge transfer. The latter is typically a challenge in many projects as the focus many times at the end of a project is to ensure a smooth transition to the run time environment, rather than collecting and sharing project experiences. In this context it is however goal in itself to find out how the executed pilots met their respective goal, hence the emphasis on evaluation and information transfer mechanisms.

To share knowledge usually requires a systematic approach, where task are executed in a repeatable and planned fashioned, as opposed to “ad hoc”. It also requires that information entities of identified value are categorized and presented according to relevant domains.

The Pilot Execution Guidelines suggests information and areas believed to be relevant for conducting, monitoring progress and analyzing the outcome of pilots executed.

## Pilot types, overview

The Project Evaluation Guidelines will focus in providing support for conducting the following three pilot types:

- Proof-of-Concept Pilot: 
Artificial setup and not production ready. Mainly for learning and feasibility study on one or more issues on one of the EIF 2.0 interoperability levels.

- Test Pilot: 
Artificial setup, but in principle production ready. Mainly for addressing issues on several EIF 2.0 interoperability levels.

- Production Pilot: 
Real life set up, but not rolled out (into a production environment). Mainly for addressing issues on all EIF 2.0 interoperability levels.

## Pilot types, details

Proof-of-Concept Pilot

- Narrow scope - only one part of an interoperability level in EIF 2.0 is addressed (technical, semantic, process).

- Artificial setup - there’s no impact on organizations and its production system when running the interoperability model.

- Still old processes in production

- Interchange of information is one to one

- Small number of participants

- No focus on quality

- Short lifetime of pilot (less than one month)

Test Pilot

- Medium scope - Not all interoperability levels in EIF 2.0 is addressed (technical, semantic, process)

- Artificial setup there’s no impact on organizations and its production systems when running the interoperability model.

- Still old processes in production

- Interchange of information is one-to-many (or many to one)

- Small to medium number of participants

- High focus on quality (testing)

- Medium lifetime of pilot (1-3 months)

Production Pilot

- Large scope - All interoperability levels in EIF is addressed (technical, semantic, process, organizational, legal)

- Real life setup - impact on organizations and its production systems when running the interoperability model.

- No parallel (old) production processes

- Interchange of information is many to many

- Medium to large number of participants

- High focus on quality (testing)

- Long lifetime (3-12 months)

The different scope and objectives of the various pilot types will obviously affect the composition and overall need for project evaluation guidelines and project support. A checklist that will assist in assessing the necessary efforts of each pilot type is provided in this document. For more information, see section “Pilot Execution Checklist”.

## Assumptions

The assumptions valid for the pilot execution template and pilot report are that they should:

- be generic and based on best practices

- allow for eProcurement-specific adoption and – if necessary – extensions and/or adjustments.

- generate a small footprint

- assist in the facilitation of a framework for pilot support that is flexible, yet sufficiently comprehensive to allow for the maintenance of critical relationships, such as risk, budget, delivery, task completion, quality assurance and specific profile support.

- consider and support any type of project methodology and development model considered and selected for the upcoming pilot implementation. An unbiased approach is therefore used.

# Building blocks

The building blocks are those entities that together need to be covered in the project template and, in general, those that will be presented in the project report. As such, the “building blocks” are in effect the suggested level 1 headlines of the project plan. The below list serves as a starting point for finding out those entities that together forms the “project” – the requirements for a project template and project report.

## Pilot template Requirements

- Requirements

  - High level (Business requirements)

  - Functional

  - Non-functional

  - Use Cases

  - Profile(s)

- Goals and objectives

  - Project goals

  - Product (solution) goals

  - Effect goals

  - Success criterion

Note: It is recommended that Key Performance Indicators (KPI:s) are used and set for the measurable goals defined for the project. This will help in monitoring the success of the project as the work progresses. Outside linking KPI:s to the success criterion, an obvious measure, KPI:s should also be linked to the project related entities such as delivery dates, milestones and other elements of the project.

- Evaluation criteria (in effect the “indicators” of the success criterion)

Note: see also the Evaluation Guidelines for further reading and suggestions on how to link overall project (pilot) objectives to requirements and measurable elements.

- Tools

  - Project tools

  - Development tools

  - Quality assurance and test tools

  - Life cycle management tools

  - Governance tools

- Profiles

- Risk list

- External planning elements (either included in the project plan or referenced, depending on scope and complexity)

  - Test plan (see also the Test Guidelines)

  - Iteration plan

  - Implementation plan (transition plan)

- Documentation

  - Project documentation

    - Minute-of-Meetings

    - Progress reports

    - Value creation reports, possibly based on the “earned value” method.

  - Artefacts and deliverables as defined in the project (pilot) directive at the inception of the project (pilot)

- Task breakdown

  - Work items

- Resources

- Stakeholders

- Commercial considerations

  - Budget

  - Earned value

  - Constraints

- Timeline

  - Considerations

  - Baseline

  - Deadlines and toll gates

  - Delivery dates

- Lessons learned

  - An important aspect of the project evaluation guidelines is obviously to capture lessons learned. Lessons learned will as suggested in this document will be included in all reports, independent on scope of the pilot executed.

Note: In terms of project report, there is probably a need for several different project reports, as the various stakeholders of the project might typically have different need for monitoring the status and progress of the project.

Comment: The above list is subject to scrutiny and completion.

The elements of the project template can also be further organized according to the following classification:

- Goals

- Requirements

- Plans

- Reports – Status

- Etc.

## Pilot report

In general, the layout of the pilot report should reflect the status of and cover the major building blocks of the project (in line with the list of entities provided in the previous section). A clear difference however is that the project report normally will provide a “snap shot” of the current situation and, where applicable, a forecast of the upcoming situation where possible and desired based on the current state of affairs.

The project report can also be composed according to several different principles:

- To summarize the status of ALL /critical/ entities of the project

- To summarize the critical activities with reference to separate more detailed reports (e.g. test reports, task execution reports, budget reports etc.)

The project report should at a minimum be used to track “show stopper” activities, critical to the success (or failure) of the project.

The project report should also allow for tracing and implicitly – in retrospective – analyzing the progress, not just from one report to another, but also throughout the duration of the project (inception to exit).

# Methodology

The actual disposition of the project template and project report is, in terms of requirements, intimately linked to the methodology used for project execution (project method) as well as development model. Depending on selected methodology, the project template and project report will need to be developed according to the baseline of the method in question.

Assumptions on project methodology:

- Project: An iterative and incremental project methodology will be selected.

- Project: The selected methodology will adopted and, if needed, adjusted to fit the specific demands of a pan-European eProcurement pilot.

- Development: An Agile model will be used, allowing any development team involved to work according to the principles of lean development methods.

- Project and Development: Independent of the actual methods and models finally selected, it will be imperative that all parties involved in the development of the pilot share a common understanding of the method and model selected and that all resources are knowledgeable in terms of base criteria for working with the respective current activity, deliverable, task etc. at hand.

- Information: The most critical success factor might be information in terms of availability, accuracy and distribution. The project related information must be created, conveyed and processed in such a fashion that it creates value to the stakeholder of the project. Ultimately, the creation of information should to the largest possible degree be automated.

## Selecting the Project methodology

The suggested selection criterion for selecting the pilot execution methodology:

- Scope

- Past experiences and knowledge (the learning curve for any new / rarely used methodology as opposed to using a market leader and de facto standard should be considered)

- The method should be widely spread and well known (“industry /de facto/ standard”)

## Development Model

The development model should be easy to adopt and allow for usage in the context of the selected project methodology. As for the development model itself it should share the characteristics of the project methodology in terms of being lean and agile.

## Roles

The project roles should be defined. One person can often easily man several roles; the purpose of describing several roles is to simplify the division of responsibility. It might be useful to differentiate between internal (roles actively participating in the project) roles and external roles,

## Project specific considerations pertinent to the CEN BII WS and PEPPOL

In order to make the specific elements of eProcurement useful, the generic project building blocks described above must be applied on a practical and CEN BII / PEPPOL specific level. This means that all relevant entities that together form the framework (CEN BII) and pilot (PEPPOL) should be covered by the project template and project report, using the generic approach outlined in this document as the starting point for further elaboration (if necessary).

The list current list of entities subject to analysis and process the CEN ISSS BII WS and PEPPOL cover the elements listed below.

- Process support for eProcurement based on the CEN ISSS WS BII profile definitions

- Infrastructure

- Tools

  - All entities that together form the infrastructure must be targeted and monitored.

  - Any tools used to execute the solution must be handled.

## The Pilot Execution template & Pilot Report– overview level layout

In order to identify the requirements for a project template and project report, it might be useful to look at the expected input, activities, result and “exit criteria” that could be relevant for this activity.

### Input

- The Project template should consider (cover) a formal description of what is to be created – the “what” (with reference to the requirements specification, se further below) and more importantly the “how” – what activities, resources and in what order and on what dates are the necessary activities and their output expected to take place.

- The formal assignment from steering committee (or equivalent), a call to start up Inception.

- A clear definition of product and effect goals, including any measurable economical objectives.

- Expected critical dates (delivery dates, milestones) and known prerequisites for meeting the expected dead-line(s).

- A Risk list, with classification and prioritization of risks

- Business, functional and non-functional requirements

- Success criterion and indicators for each success criteria (see also the Evaluation Guidelines)

- A list of Stakeholders and Roles

- Processes, use cases and information entities to be supported, manifested as CEN ISSS BII profiles

- Any critical relationship and/or mutual dependency should be highlighted, i.e. when the delivery of a certain artifact is dependent on one (or more) activities, in turn dependent on the creation of another artifact, the provisioning of reporting such dependences should be supplied.

### Activities

- On-going: keep an updated list of the critical artifacts that together are subject for the solution

- When necessary: perform a work shop with the purpose to secure that the project plan & report actually provides necessary coverage (in terms of entities that need to be included).

- On-going: construct the project template and project report according to the requirements identified.

- When necessary: update the project template and project report according to new, outdated or modified requirements.

### Result

- A Project plan implemented on the requirements defined and agreed upon as being correct.

- A Project report implemented on the requirements defined and agreed upon as being correct.

### Exit criteria

A project plan and a project report (on or more) used by the PEPPOL project members.

### Overview level process

The below picture provides a high level view on how to use the Pilot Execution Guidelines.

Please note that the Test and Evaluation Guidelines should be used to set up and fill out the various elements of the Pilot Execution Framework with the relevant content. I

# MISCELLANEOUS

In terms of identifying the requirements for a project template and project report, it is possible to find many of those when inspecting the proposed list of topics in a Test plan. This is quite obvious, since the test plan in essence should test all /critical/ aspects of the project. For further information about the Test Plan, please refer to the CEN ISSS BII WS Test Guidelines.

# Pilot Execution Templates

## Pilot Execution Checklist

To allow for the necessary flexibility the Pilot Execution Guidelines includes an execution checklist. The checklist proposes the necessary elements that need to be in place before conducting the pilots. The scope is determined by the type of pilot.

| Notes: |  |  |
| --- | --- | --- |
| 1 | The elements are explained below. |
| 2 | An "X" marks a required element. An "(X)" marks an optional element. |
| 3 | The "in place" column can be used to trace when an element of the required project setup for the pilot at hand has been created. |
| Note: | Several of the “elements” above might be grouped to a single container (document) – in other words, it’s possible to keep several elements together; each single element doesn’t require a document or report. |

### Legend

| Item | Explanation |
| --- | --- |
| Effect & Goal statement | Provides that rationale (background) and expected goals for the pilot to be executed. The goals might be stated on high level, preferable with links to the functional and non functional requirements and/or profiles that form the basis for the pilot in question. |
| Project Definition Report | Defines the scope of the project and outlines major elements in terms of dates, resources and expected result. |
| Project contract | A project contract is a document that contains a set of various agreements that underlie a project. |
| Project plan | The project plan is a detailed description of activities, milestones, dependencies, resources and deliverables. The Project plan links tasks and activities to dates and resources. |
| Change Request Form | The change request form is used to describe changes to any project element, e.g. activities, deliverables or resources. |
| Change Log | The change log is used to keep an audit trail of any changes made to the project from the inception to the end of the project. |
| Issues Log | The issues log is used to keep an audit trail of any issues related to the project from the inception to the end of the project. |
| Risk Log | The risk log is used to keep an audit trail of listed project related risks from the inception to the end of the project. |
| Progress Report | The progress report is used to successively describe how the project progresses. By keeping the progress report up to date, the creation of the lessons learnt report is facilitated. |
| Milestones Report | The checkpoint report focuses on reporting on critical activities - toll gates and milestones. |
| Customer acceptance form | The customer acceptance form lists requirements that need to be verified and fulfilled in the final product / solution. By signing the acceptance form the customer (or main stakeholder(s)) approve that the project goal has been achieved. |
| Project Closure Report | In this report, any activities and closing remarks are entered and subsequently verified. |
| Lessons Learned Report | The lessons learned report is a compilation of the accumulated experiences gathered during the project. The lessons learned report should be measured against the effect & goal statement and project contract. Input consists of change, issues and risk log as well as the progress and checkpoint reports. |
| Budget Justification Template | The budget justification template can be used to enter economical incentives for the project, such as excepted return on investment (ROI), total project budget, cost divided on project element (resources). If necessary |
| Functional Requirements Specification | Lists functional requirements (or, alternatively, profiles) |
| Technical Requirements Specification | Lists non-functional requirements |
| Stakeholder Management Plan | Lists stakeholders and their respective interest in the project. Link any necessary information and other element to each individual stakeholder |
| Work Breakdown Structure | Activities are broken down and individual tasks, linked to individual project member. |
| Funding Proposal | Describes how the project is funded or, if thus far lacking funding, proposes funding. |
| Test plan | Lists necessary test & quality assurance elements. Alternative, reference the Test Guidelines (see Test Plan) |
| Mitigation report | The mitigation report is used to keep track on the activities following the identification of a pilot risk element. This item might be integrated into the Risk log. |

Comment:

The above list of suggested elements to consider might be perceived as overwhelming in scope. All items are however suggested based on best practice. It should also be pointed out that scope is determined by type of Pilots. Further corrections in terms of additions and reductions to the check list should be made based on first hand experiences as the pilots are executed.

## Selecting the appropriate content

To select the appropriate pilot content in terms of scope is as pointed out in previous sections dependent on the scope of the pilot. The high level needs are illustrated by the pictures depicted in the following sections.

### Proof-of-concept Pilot

PoC Pilot: the PoC pilot in general puts emphasis on project management before and after the actual pilot execution phase.  The purpose of the Proof-of-concept is usually to verify a certain element, for example a profile or an element of a profile (for example a collaboration).

Instructions:

- Use the templates of the Evaluation Guidelines to setup and enter the objective statements and Key Success Indicators (metrics).

- Use the Pilot Execution Guidelines to enter the necessary information for the appointed elements before and after the Proof-of-Concept Pilot has been executed.

### Test Pilot

The Test Pilot: the typically larger scope for the test pilot consequently calls for more attention to most if not all of the project elements included in a “full scale” project. The objective of a Test Pilot might be to verify the interaction and complete information flow of profile or, for that matter, several profiles. The purpose might also be to verify that the infrastructure supports the profile structure as expected. The requirements in terms for Pilot Execution support are therefore markedly higher than in the case of the PoC.

Instructions:

- Use the templates of the Evaluation Guidelines to setup and enter the objective statements and Key Success Indicators (metrics).

- Use the Pilot Execution Guidelines to enter the necessary information for the appointed elements before and during running after the Test Pilot and after that the Test Pilot has been executed.

### Production pilot

Production pilot: the extended nature of the Production Pilot calls for a comprehensive project execution, where transition related aspects such as production roll out, inherent governance features, life cycle management features and other “real life” attributes are given additional attention. The Production Pilot’s exhaustive cover typically also requires more focus on planning (setting up the pilot) as well as a successive and iterative surveillance and adjustment as the work progresses.

Instructions:

- Use the templates of the Evaluation Guidelines to setup and enter the objective statements and Key Success Indicators (metrics).

Use the Pilot Execution Guidelines to enter the necessary information for the appointed elements before and during running after the Production Pilot and after that the Production Pilot has been executed.

### General remarks

- Please refer to the Evaluation Guidelines for more information on how to set up the Evaluation Guidelines based elements.

- In terms of Pilot specific considerations: the “Do, Study, Act” element of the Pilots – with degree of iteration determined by the scope of the Pilot – is especially critical in order to obtain the information necessary in order to fine tune the elements subject to Pilot execution as well as the frameworks that give support for executing the individual Pilot.

- Please note that any element of the Pilot Execution Template linked to a specific Pilot phase (pre Pilot, during Pilot execution or Post Pilot) might be subject to revision in more than “just” that specific phase. The Project plan, for example, is typically continuously updated and revised.

- An audit trail should be kept for all elements of the Pilot Execution Guidelines subject to revision / change.

## Pilot (Project) Template

The pilot template is high level element used to define a Pilot. Use the sections below as guidance and fill out each section with the relevant information. Use the matrix to understand when it’s recommended to use what section.

### Instructions

This template is used as the basis to enter relevant information for the different Pilot types covered by the Pilot Execution Guidelines (PEG). The template is organized as a high level checklist. Follow the steps provided below to create the appropriate Pilot set of information in support of Pilot execution.

### Step 1: Select Pilot Type

- Select the pilot type 
- Proof-of-Concept Pilot
- Test Pilot
- Production Pilot

- If necessary: make necessary adjustments in terms of PEG elements to exclude or add. Create a Exception report that lists the motives for the changes.

### Step 2: SET UP (Pre Pilot)

In this step the necessary PEG elements that together provide the required background and rational for the Pilot are completed.

For all elements listed below, the suggested usage in terms of Pilot type is listed in parenthesis according to the following legend:

- “PoC” – denotes “Proof-of-Concept Pilot”

- “T” - denotes “Test Pilot”

- “Prod” – denotes “Production Pilot”.

Note: Most elements created in this step will be used throughout the duration of the Pilot (in all steps).

It is suggested that the elements listed below are grouped together when found appropriate. The basis for grouping might be:

- Scope (type of Pilot)

- Roles (# of roles involved in the Pilot)

- Complexity and level of technology

For example, when grouping the PEG elements together, it might be recommended add those elements related to management (e.g. Project Management) together, those related to configuration management and change requests together and so forth.

#### Effect & Goal Statement (Poc, T, Prod)

Provides that rationale (background) and expected goals for the pilot to be executed. The goals might be stated on high level, preferable with links to the functional and non functional requirements and/or profiles that form the basis for the pilot in question.

Typically, a production pilot will have a more elaborate effect description, while the Proof-of-Concept will be focus on a single task and goal.

#### Project Definition Report (Poc, T, Prod)

Defines the scope of the project and outlines major elements in terms of dates, resources and expected result.

This report should provide a summary overview of the pilot at hand. Suggested composition:

- Scope

- Start date and expected end date

- Staff (resources)

- Purpose and expected result

#### Work Breakdown Structure (Prod)

Activities are broken down and individual tasks, linked to individual project member. This element is typically inserted into the Project Plan.

#### Funding proposal (Prod)

The funding proposal defines how the project is funded or, if thus far lacking funding, proposes funding. This element might typically refer to a separate document, but is still important that the funding (budget) is known before initiating the Pilot.

#### Test plan ((T), Prod)

The test plan lists necessary test & quality assurance elements and tasks. Reference the Test Guidelines for further information (see “Test Plan”). It is important that the Test plan is composed before the actual Pilot activites during the execution phase commences.

#### Functional Requirements Specification (T, Prod)

Lists functional requirements (or, alternatively, profiles).It is possible – preferred - to refer to any specific profile(s) in place of entering separate requirements.

#### Technical requirements specification (T, Prod)

Lists non-functional requirements, preferably categorized according to any a the industry based best practice such as FURPS+.

#### Project contract (T, Prod)

A project contract is a document that contains a set of various agreements that underlie a project.

#### Project plan (Poc, T, Prod)

The project plan is a detailed description of activities, milestones, dependencies, resources and deliverables. The Project plan links tasks and activities to dates and resources.

#### Change Request Form (T, Prod)

The change request form is used to describe changes to any project element, e.g. activities, deliverables or resources.

#### Change log (T, Prod)

The change log is used to keep an audit trail of any changes made to the project from the inception to the end of the project.

#### Issues log (T, Prod)

The issues log is used to keep an audit trail of any issues related to the project from the inception to the end of the project.

#### Risk log (T, Prod)

The risk log is used to keep an audit trail of listed project related risks from the inception to the end of the project.

#### Mitigation report (T, Prod)

The mitigation report is used to keep track on the activities following the identification of a pilot risk element. This item might be integrated into the Risk log.

### Step 3: Execution

This is the main pilot phase where most of the actual work involved in running/executing the Pilot is done.

#### Progress report (T, Prod)

The progress report is used to successively describe how the project progresses. By keeping the progress report up to date, the creation of the lessons learnt report is facilitated.

#### Milestone report (Prod)

The checkpoint report focuses on reporting on critical activities - toll gates and milestones.

#### Stakeholder Management Plan (Prod)

The Stakeholder management plan lists stakeholders and their respective interest in the project. Link any necessary information and other element to each individual stakeholder.

### Step 4: Post Pilot (Follow up)

In terms of gaining experiences and learning from the Pilots, this step of the Pilot execution is obviously the most important. By collecting information from the various PEG elements that have been compiled during the Pilot’s life cycle, the actual evaluation of the Pilots ultimately goal should be possible to understand without any major efforts.

#### Customer Acceptance form (Prod)

The customer (stakeholder) acceptance form lists requirements that need to be verified and fulfilled in the final product / solution. By signing the acceptance form the customer (or main stakeholder(s)) approve that the project goal has been achieved.

#### Project closure report (T, Prod)

In this report, any activities and closing remarks are entered and subsequently verified.

#### Lessons learned report (PoC, T, Prod)

The lessons learned report is a compilation of the accumulated experiences gathered during the project. The lessons learned report should be measured against the effect & goal statement and project contract. Input consists of change, issues and risk log as well as the progress and checkpoint reports.

## Pilot (project) report template

The pilot report template is be used to provide a summary of the current status of any pilot running. The pilot report is in essence a progress report that summarize how the pilot progresses. The main focus is to highlight any area issue area so that the pilot management might act on the issues.

The main entities of the pilot report template are:

  - Date

  - Pilot id

  - Project manager

  - Version #

  - General comments (free form)

  - Management view (executive summary)

  - Change requests status

  - Quality level summary

    - # of defects

    - Mitigated defects

  - Risk summary

  - Mitigation summary

  - Timetable status

  - Covered and outstanding main tasks

The Pilot report serves as a “snap shot”.

The Pilot (Project) report template is attached as a separate Report Annex to the WG4 CWA

## Project plan Template – alternate Example

Below is an example of a project plan template used for traditional software projects. The intention is NOT to propose that pilot plan template present above should be replaced, but to illustrate how a project plan template alternatively could be manifested. Look as this alternative example as “inspirational”.

Comments have been inserted to provide further clarification where the heading / content is not self explicatory. The project plan example is not to be viewed as a proposal, but rather as an example. Considering the PEPPOL pilot scope and content there are sections omitted in the below example, as well as sections that either are included in other documents or all together unnecessary / out of scope. Hopefully, though, the example will aid in finding out the any missing elements when composing project template and a project report.

Project Plan Example

Version 2.2

Edition 1

| Document ID: | <document name goes here> |
| --- | --- |
| Author(s): | <author> |
| Reviewed by: | <revised by> |
| Date: | <date goes here> |

Comment: To have the project plan revised is recommended (if not required).

Revision History

| Date | Modifications | Reason | Version |
| --- | --- | --- | --- |
| 1999.04.07 | Various sections combined (AK) | Initial document collation | 0.1d |
| 1999.04.08 | Document contents formatted (AK) | Conformance to Style Specification | 0.3d |

Table Of Content

| 1. System Development Plan 1.1 Major Milestones 1.2 Gantt Chart 1.3 Procedures 1.3.1 Requirements Analysis 1.3.2 Verification 1.3.3 Requirements Document Development 1.3.4 Validation 1.3.5 Solution Analysis 1.3.6 Product Specification and Design 1.3.7 Product Implementation 2. Configuration Management Plan & Procedures 3. Development Support Environment 4. Verification & Validation 4.1 Testing Plan Introduction 4.1.1 Testing Plan Purpose 4.2 Testing Plan Scope 4.3 Lifecycle Phase Independent Activities 4.3.1 Critical Analysis and Risk Assessment 4.3.2 Document Review 4.4 Lifecycle Phase Dependent Activities 4.4.1 Analysis Evaluation 4.4.2 Design Evaluation 4.4.3 Software Development Evaluation 4.4.4 Test Evaluation | 5. Quality Assurance Process Plan 6. Documentation Plan 6.1 Document Completion Procedure 6.2 Transfer Procedure 6.3 Feedback 7. Delivery Plan 7.1 Project Deliverables 8. Distribution Procedure 8.1 Deliverable Distribution Procedure 9. Marketing Plan 9.1 Solution Advertisement |
| --- | --- |

1. System Development Plan

1.1 Major Milestones

The milestones have previously been defined in the <milestone definition> document. The following table lists the milestones in relative chronological order along with their dependent tasks, the number of people working on them, and the date they are due.

Comment: The actual Milestones as well as number of resources and due dates are only provided as examples.

| Milestone | Milestone description | Dependency | Resources | Due Date |
| --- | --- | --- | --- | --- |
| 1 | Requirements Analysis | 0 | 7 | 30 October 2008 |
| 2 | Verification | 1 | 4 | ongoing |
| 3 | Validation | 1 | 4 | ongoing |
| 4 | Requirements Solution Statement | 1 | 7 | 30 November 2008 |
| 5 | Requirements Refinement | 2 | 5 | ongoing |
| 6 | Solution Analysis | 3 | 7 | TBD |
| 7 | Pilot Specification & Design | 4 | 7 | 30 January 2009 |
| 8 | Pilot Implementation | 5 | 7 | TBD |
| 9 | Pilot Testing | 8 | 4 - 6 | 30 April 2009 |

Table 1.1 - 1: Major Milestones

1.2 Gantt Chart

The schedule as outlined below only defines the first five tasks be completed. For each task, there is one or typically more work items defined.

Note that the verification and validation tasks here only indicate the processes in regard to the functional prototype, not the final pilot. This is why in the above milestones chart they are listed as ongoing (open ended) and here we state their start and end dates.

<Gantt chart goes here>

Figure 1.2 - 1: Gantt Chart

In the above chart, color coded bars might indicate the planned start, duration and end dates while another color represented bar might represent the "slack" time in which we can finish the task without adversely affecting the time specified for later tasks. This might provide better exposure to task that have large adverse impact on the project.

1.3 Procedures

1.3.1 Requirements Analysis

In order to build the correct pilot the given requirements need to be analyzed in detail. The business requirements statement typically only specifies the broad idea regarding what functionality the system needs to provide. From this we need to flush out what is needed and what is not on a more specific level.

In order to do this effectively a functional prototype will be implemented.

The prototype will assist in verifying that the thus far defined requirements are correct, comprehensive and specified at the necessary level of detail. The prototype will also provide insight into the qualities of the proposed infrastructure and the technologies required to implement the requirements. The prototype will also provide an opportunity to establish development and quality assurance processes.

1.3.2 Verification

Verification is the process of determining whether the right solution is being developed. Once a prototype is complete the result of the prototype will be analyzed with the main objective to verify that the requirements have been satisfied in the prototype. This will involve an iterative two step process:

1   Determine what's missing or not required

2   If updates still required

2.1   Update the prototype

2.1.1   Return to step 1

2.2   Otherwise stop verification

It should be noted that verification is an ongoing process. At the each completion of each milestone, we will need to perform a verification analysis to make sure we are still on track. Similar to the above process, this will be in conjunction with the reference group.

Following the completion of this verification phase, it should be possible to begin defining the pilot we intend to build more precisely. This will be in the form of the Requirements Solution Statement.

1.3.3 Requirements Document Development

The requirements solution statement is an abstract definition of the functional and non-functional requirements of the system as interpreted. It will serve as the contract between the pilot <supplier> and the <commissioning body> by defining exactly what to develop and on what basis (standards, profiles, functional and non-functional requirements). The requirements document also serves as a basis for QA to develop testing procedures for the development/testing phase of the project.

Comment: the “Requirements document” is the collective name for what in effect very well could be an aggregate document, referring to several artifacts / documents.

Note: each major task / phase of the project will require a verification process, similar to that of the prototype verification. The purpose, to secure the result and level of quality, is basically the same, independent on type of task / activity.

1.3.4 Validation

Validation is the process of making sure that the solution is constructed correctly and according to the requirements specification (including legal and non-functional specifications). Throughout development of the pilot, weekly builds of the solution will be declared and handed to the Quality Assurance (QA) team.

QA will then perform various testing procedures on the product and present the defects to the development supplier(s) to mend. Once all the defects found by QA have been fixed, another build is declared and the process repeats itself.

The actual testing process is defined more precisely in the <Implemented Test Guidelines document>.

1.3.5 Solution Analysis

Once we have our final solution statement, we need to design the final solution. Given that we have already built the functional prototype by this stage, we should have a good idea as to how to go about building the system.

As a result of building and analyzing the prototype it should be possible to determine:

- what worked well

- what needs to be redesigned

- what needs to be thrown away altogether

- what needs to be added.

This will form the basis of the Solution specification and design.

Note: In order to avoid confusion, it should be pointed out that the term “pilot”, above, and “solution” from this section and beyond might very well be interchanged, as the “pilot” (in the case of PEPPOL) is in fact the “solution”, that is the final result – the solution/product.

1.3.6 Solution Specification and Design

The Solution Specification and Design will be based on the solution statement and solution analysis. It will include implementation specific information such as class diagrams, object models and so forth. At this stage the specification and design process is relatively undefined. As the project develops more information will become available.

1.3.7 Solution Implementation

As above, the process of implementation will become clearer as it comes closer and will be defined at a more appropriate time. 
  
Note: The following section assumes that the PEPPOL pilot will be build in a “traditional” and solution oriented fashion. This might very well NOT be the case. The PEPPOL pilot might in fact be based on and assembled by various entities and building blocks, both traditional products (software) and services, available in the cloud and/or through on-site secure channels accessible at the the appointed suppliers’ and/or clients’ respective environment. The need, however, for CM and defined procedures is assumed to be unaltered.

2. Configuration Management Plan & Procedures

From the point where there is a functional user interface skeleton, builds will be made at intervals set by the Application Engineer (or similar role).

Each build will be a tagged version, named sequentially build-1, build-2, etc. These builds are sent to the Quality Assurance team (QA) and if they are deemed suitable to be released as versions, they are released as internal versions. The criteria used by QA to determine what qualifies as a version is specified in this document under the QA and Test Plan sections (alternatively referenced – with reference to the external Test plan).

When /new/ versions are to be constructed, they will be named sequentially version-1, version-2. These builds and versions will be performed by the Configuration Manager. Any problems should be reported to the Application Engineer (author) and the Configuration Manager.

Instructions on checking out builds and versions will be published when the first build is created. The build and version numbers are for internal use only and do not relate to the public releases. These will be made at the discretion of the Application Engineer and subject to quality assurance approving a build. These will be given names such as 'Cohesion' and 'InSync'

Projected release dates will be published by the Application Engineer when they become available. 
  
3. Development Support Environment

The software development environment is a suit of applications which allow quality software to be written in a flexible way. All of the development software is available at the <development site/sites>. The following software is supported:

- <List of software used for development>

- Example (note: partially fictional):

  - Windows Vista

  - SUSE Linux version 3.0 or higher

  - Java 6 JDK from Sun Microsystems, Inc.

  - JRE 3.0from Sun Microsystems, Inc.

  - Notepad

  - Symantec Visual Cafe 6.0

  - JBuilder 5.0

  - Visual Studio Team Suite 2.0

Developers are free to use other development tools. Before any code is checked in to the repository, it must compile using the supported tools. Developers may not receive support for problems caused by using unsupported tools.

As new tools become available and are tested, they may be added to the list of supported software.

The software listed above requires for following minimum system hardware specification to run:

<The minimum Hardware specification goes here>

Any system not meeting this requirement will not be able to install and/or run the required software.

Development under other operating environments and or operating systems is not supported. It may be possible to develop and build under the Solaris OS, or on private Linux installations, but this is not supported and any problems must be solved by the individual developers. All code developed under these environments must be tested under the supported environment before being checked in to the repository.

4. Verification & Validation

4.1 Testing Plan Introduction

4.1.1 Testing Plan Purpose

The purpose of this Verification and Validation Plan for the pilot, is to document the planned steps taken by <the project group> to ensure that the solution developed is of high quality in relation to what the <commissioner> has requested. In other words, it assures that we take steps so that:

- We build the right solution.

- We build the solution right.

4.2 Testing Plan Scope

Please see Report 1, requirements for Test Guidelines for further information.

4.3 Lifecycle Phase Independent Activities

Lifecycle Phase Independent Activities might be outside of the scope for the PEPPOL pilot. It is, however, recommended that the solution is built in such a way that lifecycle specific considerations are at least considered and if possible built into the solution. This might include (but not be limited to):

- Built-in status check reporting

- Built-in monitoring and alert handling

- Built in near-real-time analysis and reporting

- Built in change management

4.3.1 Critical Analysis and Risk Assessment

Analysis and mitigation of risk is an integral and critical part of the project reporting. The project manager (or, if the necessary, the risk manager role) is responsible for maintaining the risk list as well as securing that all critical risks are highlighted and that activities to mitigate risk are planned and executed.

4.3.2 Document Review

Documentation reviews are conducted to observe measurable progress in the software completion process by reviewing and analyzing delivered solution design and development documentation. There are three kinds of document reviews conducted by the project team, namely:

- Document revisions received via the Customer as a Configuration Change Request (CCR). The project team’s responses might be submitted in the form of Impact Analysis Reports. An example may be a CCR proposing changes to Level 3 requirements that could present a potential impact to the detailed design.

- Checking for missing documents. This occurs when extra requirements or extra wanted functionality is received from the Customer. The goal is to secure that all Change Requests are fully analyzed and that no activities are initiated without a clear definition of what is to be done (I e a functional and/or non-functional requirement specification).

- Checking for redundant documents or document sections. This occurs when requirements or functionality wanted is removed by the Customer.

Note: “Customer” in this context could be replaced for “steering committee” or “commissioning party” (or equivalent),

4.4 Lifecycle Phase Dependent Activities

If applicable (see the comment above), further Lifecycle specific activities might need to be planned and executed, such as:

- Analysis Evaluation (Prototyping)

- Design Evaluation

- Software Development Evaluation

- Test Evaluation

4.4.1 Analysis Evaluation

Analysis evaluation consists of examining both the process used when the project team performed the analysis for the solution and the actual requirements generated by the effort. Then, these requirements are compared to the known requirements received from the Customer, and the functionality required by the Customer.

4.4.2 Design Evaluation

Design Evaluation consists of examining both the process in which <the development team> produced the design for solution and the actual deliverables generated by the effort. Follow-on design analysis will focus on reviewing the progress of software development processes and changes, and enhancements to design the solution (and whatever entities that together form the solution).

4.4.3 Software Development Evaluation

Software Development Evaluation consists of analyzing software code and related documents to assess whether the implementation is traceable to the design and of high quality. The solution will also be checked for standards compliance, internal code consistency, appropriate functionality, and support of desired user interaction, as appropriate.

The Solution Development Evaluation is primarily solution oriented (I e focus is examination of software code); however, the implementation of software development processes (e g. adherence to any development standards used) will be examined also.

4.4.4 Test Evaluation

Test Evaluation consists of the witnessing and independently analyzing results of system tests performed by the QA Team. The following process in performing test evaluation could be used:

- Obtain system test and verification plans, and test schedules.

- Review plans for sufficiency and completeness of test coverage and requirements traceability.

- Identify tests to witness, critical requirements.

- Witness tests.

- Analyze test results provided by the QA Team to assess test conduct compliance to plans and procedures, and to verify that the results accurately and completely reflect the outcome of the tests.

The Test Process Evaluation focuses on how the QA Team test process is implemented. The evaluation examines the test plans for the system as well as the verification plan, and the system integration and test plans to assess the likelihood that the process will (continue to) yield the required implementation end solution. 
  
5. Quality Assurance Process Plan

This document describes the following:

- The structure the <team goes here> will work in.

- The procedures and protocol the <team goes here> will follow.

- Assumptions and expected standards from other <team goes here>.

- Actions taken for possible issues or scenarios that may arise.

5.1 QA Team

<Description of one team – could be applied on any team part of the Pilot project>

5.1.1 Team Structure

| Name | Skills | Type of work assigned |
| --- | --- | --- |
| <Name goes here> | <Skill set> | <List of responsibility and work items> Note: ultimately generated from the project report tool and/or synchronized with the development and CM tool used. |

Table 6.1.1 - 1: QA Team and Responsibilities

5.1.2 Team Meetings

The <team name> will be meeting weekly at 16.30 on Monday to discuss ongoing work and problems that may arise. These meetings are compulsory for all QA team members.

Conference calls are scheduled for each Friday at10.00.

5.2 Documentation

Formal deliverable documents written by the project team will be reviewed by a QA team member for content correctness and completeness according to:

- The user requirements and defined goals.

- The analysis and design outcome.

- An expert peer reviewer’s opinion (may be a member outside the QA team, if the expert knowledge is lacking within the QA team regarding the document subject).

Non-content related issues, such as the spelling, grammar and style of document, are to be checked by the ..<if applicable>.

5.3 Internet Site

The project Site set up for the PEPPOL pilot will be reviewed by one or more QA team members for content correctness and completeness according to:

- The user requirements.

- HTML Style Guide.

- An expert peer reviewer’s opinion (may be a member outside the QA team, if the expert knowledge is lacking within the QA team regarding the document subject).

Non-content related issues, such as the spelling, grammar and style of website, are to be checked by the <if applicable>.

For the functional aspects of the project Internet Site, software testing procedures will be followed according to the procedures and issues detailed in <list of procedures goes here / is referenced here>.

5.4 QA Release Software

The following section outlines the procedure for and the standards expected for the release of software to be tested.

5.4.1 Procedure for Releasing Software to QA

- <List of procedures goes here>

6.4.2 Standard of QA Release Code

Any code that is released to QA must adhere to the following standards:

- <List of release code standards goes here, if applicable>

5.5 Testing Process

This section describes the procedures QA will follow in order to assure a complete and unbiased testing of the solution. Please reference the Report 1 – requirements for Test Guidelines for further information.

5.5.1 Procedure for Testing

For each section of the solution to be tested, the following steps will occur:

- <Procedure list goes here>

5.5.2 Issues Relating to the Testing Procedure

The following are issues relating to the process of the QA Team:

- <Procedures for  the QA team>

5.6 Bug Notification

The <bug report system> tracking system will be used for logging, viewing and editing bugs. The information on each bug logged will be as follows:

- Example:

- Date and time found.

- The component name (I e the Client Class).

- The software version.

- Concise description of the problem.

- Type of bug (I e Interface).

- Severity of bug using scale of 1 - 5 [1: Fatal error; 3: Non-fatal functional error; 5: Cosmetic errors (ie. No on-line help content)].

- Long description of test step, behavior and result.

- Current state: Not fixed, Open (I e being fixed), Fixed.

5.7 Test Cycle Completion and Iteration

Each test cycle will be iterative. To move on to the next test cycle, either no bugs or only bugs of severity 5 must be present.

There must be no bugs logged in the Internet Site bug tracking system before any stress or performance testing can be commenced.

5.8 Code Inspections

All code inspections will be performed according to the Software Inspection Process document obtainable from the QA Team Leader.

6. Documentation Plan

6.1 Document Completion Procedure

The various steps to be followed for a given document to be completed are as follows:

- The content of a document should be supplied to the project manager <or appointed responsible manager> by the group that is responsible for the document.

- A draft is written of the document and is checked and verified for compliance with the Document Style Standards defined in the project documentation plan. At this stage the document should also be given a Version number and a document ID. 
 Note: The draft should use the generic document template. This template contains the proper formatting and style according to the Document Style Standards.

- The document is then passed from the <responsible role> to the Quality Assurance Team.

- The Quality Assurance Team checks and verifies the documents for compliance with their standards.

- The document is returned to either the <responsible role> or the group that initiated the document (for content related issues). Feedback on corrections or improvements to be made before the final draft should be supplied.

- Repeat steps 3 to 6 until no further corrections/improvements are required for the deliverable.

6.2 Transfer Procedure

To ensure that a document has been transferred from one sub-group within the project to another and that each group is aware of the transfer the following steps must be adhered to:

- A copy of the document, in HTML format, is placed in the 'docs' module of the project internet site, documents folder and sub folder, according to topic / activity.

- An email is generated to the entire project group (to inform them of the completion and handover of the document), the entire Quality Assurance Team (whose members will be delegated the task of checking the document by the Quality Assurance Head). The email will contain the following information:

  - Document ID

  - Author

  - Filename

  - Version number

  - Corrections/improvements made (only relevant if Quality Assurance has already seen the document and had sent it back for corrections)

  - Any necessary comments.

- Finally the milestone, deliverable, task or work item associated with the document should be transferred between the appropriate groups in the <project report system> (if available).

6.3 Feedback

Once the Quality Assurance Team has checked and verified the document for compliance with their standards, the changes are registered in the project log book.

7. Delivery Plan

7.1 Project Deliverables

For a deliverable to be ready for submission, it must have first followed the procedures outlined in the Documentation Plan. This process verifies that the deliverable has met the Quality Assurance plan (which included being subjected to the necessary test steps). Finally, the deliverable is published on the project web site and an email is sent to the assessor.

| Deliverable | Due Date | Criticality |
| --- | --- | --- |
| <Deliverable goes here> | <Date goes here> | <Impact value> |

Table 7.1 - 1: Major Deliverables 
  
8. Distribution Procedure

8.1 Deliverable Distribution Procedure

When a given deliverable is ready to be released, the following steps are to be taken:

- <Description of the release plan>

9. Marketing Plan

9.1 Solution Advertisement

<If applicable, describe how the pilot is to be advertised, including any marketing efforts>.

# Footnotes

The Earned Value method is defined as “A methodology used to measure and communicate the real physical progress of a project taking into account the work complete, the time taken and the costs incurred to complete that work." (source: Project Magazine). To use the Earned Value method or similar method will ensure project progress transparency.

In the case of the CEN ISSS BII elements, a reference to the profile(s) might replace the need for a separate Functional requirements specification, as the Profile description captures the underlying functional requirements.